## Sheet1
Risks (R) / Opportunities (O) | Potential Financial Impact | Response / Actions
Extremely high temperatures (heat waves) impacting health and safety of the workforce and execution of contracts (R) | ☾Increase in indirect costs, such as increased medical costs, lost workdays, and project delays ☾Negative impact on execution due to productivity loss | ☾Site locations and central teams proactively track the weather advisories and projections ☾Enhanced heat stress management protocols across project sites by revising work schedules, introducing mandatory rest periods and providing shaded rest zones with adequate hydration ☾Contract schedules are adjusted in discussion with clients
Extreme precipitation impacting the safety of equipment as well as the workforce at EPC project locations (R) | ☾Increase in indirect costs to handle flooding and protect resources ☾Increased equipment maintenance or replacement costs ☾Increase in premiums for insurance policies taken for locations | ☾Site locations and central teams proactively monitor weather advisories and forecasts, making necessary arrangements to mitigate impacts at affected locations ☾Contract schedules adjusted in discussion with clients; claims filed for force majeure events
CHRONIC PHYSICAL
Risks (R) / Opportunities (O) | Potential Financial Impact | Response / Actions
Changing weather patterns, deviating from historical trends, impacting execution as well as logistics (material supply to EPC project sites and product supply to manufacturing business clients) (R) | ☾Increasingly impacting project execution causing unpredictable delays and resource allocation challenges ☾Disruptions in the construction timeline may lead to increased operational costs, potential project overruns | ☾Environment data analysed at the bidding stage as well as at the start of execution to assess such risks ☾Enhanced tracking of weather patterns during the execution phase to mitigate any negative impact
Water sourcing and availability are becoming a challenge in many locations, particularly in water-stressed regions as well as in the summer months (R) | Increased costs for water sourcing | ☾Impacted locations make alternate arrangements to ensure water availability ☾Focusing on wastewater recycling and rainwater harvesting to reduce dependence on freshwater, improving water use efficiency